## All Regions
Last Updated 11/18/2024
7 days ago --> Yesterday |  | Today --> 7 days from today
Project Status | Store Number | Name | Full Address | Market Area | New Store Notification | Test Fit | ATP Release | MPM - Market Planning Mtg | Building and Site Survey | LOI Executed | Layout Lock | Concept Lock | CapCom Approval | Lease Executed | Entitlements | CD Start | CD Delivery to SG | Building Permit Start | Building Permit End | Permit Contingency Period | Permit Pick Up | Bid Start | Bid Award | Landlord Anticipated Delivery | Possession | Ground Break | Rough-In Start | Store Lock (for Ops) | Kitchen Equip. Install Start Date | IK Install Start | Punch Walk | Temp C/O Received | Final C/O Received | Construction Completion | Turnover | Grand Opening | Real Estate Lead | Site Development Coordinator | Construction Manager | Manager of Design | Constuction Coordinator | Development Services | AOR | General Contractor | EOR | Legal | Civil Engineer | Structural Enginner | Signage
07 - Construction
| 00171 | Westfield-00171 | 221 E Broad St Westfield, NJ 07090 United States | NJ | 2023-05-24 | 2023-07-21 | 2023-09-20 | 2023-10-23 | 2023-09-27 | 2023-07-07 | 2023-11-02 | 2023-11-30 | 2024-03-25 | 2024-06-06 | 2024-02-15 | 2023-12-11 | 2024-02-20 | 2024-05-24 | 2024-07-24 | 2024-12-23 | 2024-08-01 | 2024-02-22 | 2024-04-08 | 2024-07-25 | 2024-07-25 | 2024-08-12 | 2024-08-29 | 2024-12-02 | 2024-11-26 |  | 2024-12-17 | 2024-12-16 | 2024-12-16 | 2024-12-25 | 2024-12-25 | 2025-01-07 | Pam Haber | David Behrens Lisa Donmeyer | Andrew Lehman | Alison Stewart | Oasis Mpolo |  | Jackie Durant Serinne Hong |  | Wendy Biggs Will Turnbough |  |  |  |  | 2024-12-31
| 00311 | Fishtown-00311 | 1359 Frankford Ave STE 2 Philadelphia, PA 19125 United States | PHL | 2022-06-01 | 2022-07-27 | 2022-12-21 | 2022-09-21 | 2024-08-08 | 2022-09-29 | 2023-01-16 | 2023-02-13 | 2023-06-14 | 2023-08-08 | 2023-10-19 | 2023-09-01 | 2023-10-30 | 2023-11-17 | 2024-02-20 | 2024-05-07 | 2024-07-03 | 2024-05-08 | 2024-06-21 | 2024-08-01 | 2024-07-08 | 2024-07-08 | 2024-08-12 | 2024-12-02 | 2024-11-11 |  | 2024-12-18 | 2024-12-13 | 2024-12-12 | 2025-01-02 | 2025-01-02 | 2025-01-14 | Pam Haber | Janie Schaumburg Whitney Schmidt | Andrew Lehman | Alison Stewart | Leah Bradley |  | Angela Dewar Kathryn Grotheer Sara Nobes Brian Perlow |  | Wendy Biggs Gary Hornbeck Will Turnbough |  |  |  |  | 2024-12-10
| 00180 | Farmington Valley (Canton)-00180 | 110 Albany Turnpike Suite 911 Canton, CT 06019 United States | CT | 2023-09-08 | 2023-09-29 | 2023-11-03 | 2023-10-23 | 2023-11-28 | 2023-10-27 | 2024-01-04 | 2024-02-01 | 2024-03-25 | 2024-05-07 |  | 2024-02-28 | 2024-05-06 | 2024-07-01 | 2024-07-18 | 2024-10-29 | 2024-09-27 | 2024-08-06 | 2024-09-18 | 2024-09-15 | 2024-09-30 | 2024-09-30 | 2024-10-15 | 2025-01-09 | 2025-01-07 |  | 2025-01-28 | 2025-01-24 | 2025-01-27 | 2025-02-05 | 2025-02-05 | 2025-02-18 | Pam Haber | David Behrens Lisa Donmeyer | Andrew Lehman Alex Lundstrom | Maddie Coppola |  |  | Jackie Durant Ryan Welch |  | Wendy Biggs Will Turnbough |  |  |  |  | 2025-02-18
| 00212 | Forest Hills-00212 | 106-24 71st Avenue Forest Hills, NY 11375 United States | NYC | 2023-01-18 | 2023-08-31 | 2023-12-22 | 2023-12-14 | 2024-01-11 | 2024-01-02 | 2024-01-25 | 2024-02-15 | 2024-03-14 | 2024-04-01 | 2024-05-02 | 2024-03-05 | 2024-05-02 | 2024-06-21 | 2024-11-07 |  | 2024-11-11 | 2024-05-03 | 2024-06-21 | 2024-05-31 | 2024-05-31 | 2024-10-15 | 2024-12-18 | 2025-01-09 | 2025-01-07 |  | 2025-01-28 | 2025-01-27 | 2025-01-28 | 2025-02-05 | 2025-02-05 | 2025-02-18 | Pam Haber | Janie Schaumburg Whitney Schmidt | Alex Lundstrom | Lauren Keenoy | Oasis Mpolo |  | Jackie Durant Serinne Hong Ryan Welch |  | Wendy Biggs Will Turnbough |  |  |  |  | 2024-07-01
06 - Permitting
| 00238 | Manhasset-00238 | 1593 Northern Blvd Manhasset, NY 11030 United States | NYM | 2021-03-31 | 2021-06-16 | 2021-06-09 | 2021-06-22 | 2021-06-22 | 2021-08-10 | 2021-04-24 | 2021-04-29 | 2022-01-18 | 2022-03-24 | 2023-06-30 | 2021-09-09 | 2021-10-07 | 2023-01-18 | 2023-10-04 | 2024-01-18 | 2023-10-19 | 2023-12-05 | 2024-01-10 | 2023-05-23 | 2024-12-16 | 2024-12-16 | 2024-12-31 | 2025-03-20 | 2025-03-17 |  | 2025-04-07 | 2025-04-14 | 2025-04-17 | 2025-04-16 | 2025-04-16 | 2025-04-29 | Pam Haber | David Behrens Lisa Donmeyer Whitney Schmidt | Alex Lundstrom | Lauren Keenoy | Leah Bradley |  | Jackie Durant Serinne Hong Hsienting Huang Jesus Verastegui Ryan Welch |  | Wendy Biggs Aheron Hizmo Phillip Palma Will Turnbough |  |  |  |  | 2025-04-10
| 00025 | 10th and Walnut Reno-00025 | 924 Walnut St Philadelphia, PA 19107 United States | PHL | 2022-10-06 | 2023-06-19 | 2022-10-06 | 2023-08-08 | 2022-10-27 | 2022-10-10 | 2023-06-29 | 2023-07-21 | 2023-08-08 | 2023-10-25 |  | 2023-10-03 | 2024-02-07 | 2024-03-04 | 2025-01-03 |  | 2025-03-04 | 2024-06-27 | 2024-09-13 | 2024-03-19 | 2024-03-19 | 2025-03-03 |  | 2025-02-05 | 2025-03-27 |  | 2025-05-16 |  | 2025-04-17 |  | 2025-05-19 | 2025-05-20 | Pam Haber | Erin Flatter |  | Alison Stewart | Sean Maney |  | Jackie Durant Serinne Hong Hsienting Huang Jesus Verastegui Ryan Welch |  | Wendy Biggs Will Turnbough |  |  |  |  | 2014-02-01
| 00274 | 23rd + Park-00274 | 27 E 23rd Street New York, NY 10010 United States | NYC | 2023-12-21 | 2024-02-02 | 2024-03-07 | 2024-02-26 | 2024-03-27 | 2024-02-13 | 2024-04-18 | 2024-05-16 | 2024-05-31 | 2024-06-26 |  | 2024-06-07 | 2024-07-26 | 2024-11-01 | 2024-11-27 |  | 2024-12-05 | 2024-11-01 | 2024-11-22 | 2024-12-01 | 2024-12-01 | 2024-12-09 | 2024-12-24 | 2025-05-22 | 2025-03-25 | 2025-04-09 | 2025-04-15 | 2025-04-14 | 2025-04-14 | 2025-04-23 | 2025-06-18 | 2025-07-01 | Pam Haber | Whitney Schmidt | Alex Lundstrom | Lauren Keenoy | Alyssa Bostock |  | Lucie Bechu Jackie Durant Ryan Welch |  | Wendy Biggs Will Turnbough |  |  |  |  | 2025-05-30
| 00287 | Park Slope-00287 | 76-78 St. Marks Ave Brooklyn, NY 11217 United States | NYM | 2021-09-27 | 2021-12-30 | 2022-01-12 | 2021-12-14 | 2022-01-25 | 2021-12-22 | 2023-10-26 | 2023-12-07 | 2022-08-08 | 2022-08-16 | 2024-11-24 | 2024-03-12 | 2024-08-16 | 2024-10-24 | 2024-10-30 | 2022-12-14 | 2025-02-07 | 2024-12-09 | 2025-01-07 | 2025-01-31 | 2025-01-31 | 2025-02-10 | 2025-02-11 | 2025-06-05 | 2025-05-19 | 2025-05-26 | 2025-06-24 | 2025-06-19 | 2025-07-03 | 2025-07-02 | 2025-07-02 | 2025-07-15 | Pam Haber | David Behrens Lisa Donmeyer | Alex Lundstrom | Jamie McGlinchey | Leah Bradley |  | Jackie Durant Serinne Hong Hsienting Huang Jesus Verastegui Ryan Welch |  | Wendy Biggs Josh Everett Will Turnbough |  |  |  |  | 2025-07-15
| 00214 | New Haven-00214 | 1 Broadway New Haven, CT 06511 United States | CT | 2023-08-18 | 2023-09-18 | 2024-02-27 | 2024-03-25 | 2024-03-13 | 2023-11-13 | 2024-05-02 | 2024-06-27 | 2024-07-16 | 2024-11-02 | 2024-06-27 | 2024-07-18 | 2024-09-13 | 2024-10-30 | 2025-03-13 | 2024-11-04 | 2025-03-20 | 2025-01-08 | 2025-02-20 | 2025-03-14 | 2025-03-14 | 2025-03-25 | 2025-04-09 | 2025-07-11 | 2025-07-09 |  | 2025-07-30 | 2025-07-29 | 2025-07-29 | 2025-08-07 | 2025-08-07 | 2025-08-20 | Pam Haber | David Behrens Lisa Donmeyer | Andrew Lehman Alex Lundstrom | Alison Stewart | Alyssa Bostock |  | Jackie Durant Ryan Welch |  | Wendy Biggs Will Turnbough
05 - Construction Documents
| 00008 | Bryant Park (IK Reno)-00008 | 1114 6th Ave New York, NY 10036 United States | NYC |  | 2023-11-03 | 2022-12-21 | 2023-01-24 | 2024-07-03 |  | 2024-06-21 | 2024-07-11 | 2024-03-25 | 2023-12-21 |  | 2024-07-08 | 2024-10-07 | 2024-12-02 | 2024-12-09 | 2023-12-21 | 2024-12-11 | 2024-11-18 | 2024-12-17 | 2023-12-21 |  | 2025-01-15 | 2025-01-30 |  | 2025-02-04 | 2025-01-30 | 2025-02-25 |  | 2025-02-24 | 2025-02-25 | 2025-02-26 | 2025-03-06 | Pam Haber | Lisa Donmeyer Janie Schaumburg | Johnathan Davila Andrew Lehman | Jamie McGlinchey | Alyssa Bostock Christina Brubaker |  | Michael Brandt Roberta Curtis Harlan R. Faust Eugene Taylor Scott Tieken |  | Wendy Biggs Will Turnbough |  |  |  |  | 2017-06-12
| 00105 | 56th + Broadway IK Renovation-00105 | 1740 Broadway New York, NY 10019 United States | NYC |  | 2023-11-03 |  |  |  |  | 2024-08-22 | 2024-10-24 | 2024-11-25 |  |  | 2024-11-01 | 2024-12-16 | 2024-12-19 | 2025-01-10 |  | 2025-01-14 | 2025-03-11 | 2025-04-02 |  |  | 2025-05-05 | 2025-05-20 |  | 2025-05-27 | 2025-06-04 | 2025-06-17 |  | 2025-06-17 | 2025-06-17 | 2025-06-17 | 2025-06-24 | Pam Haber | Lisa Donmeyer | Johnathan Davila Andrew Lehman | Jamie McGlinchey | Alyssa Bostock Christina Brubaker |  |  |  | Wendy Biggs Will Turnbough
| 000144 | Longwood Medical - IK Renovation-000144 | 360 Longwood Ave Boston, MA 02215 United States | BOS |  | 2024-08-19 | 2024-08-19 |  |  |  | 2024-09-19 | 2024-10-17 | 2024-11-25 |  |  | 2024-10-21 | 2024-11-21 | 2024-12-02 | 2025-03-11 |  | 2025-03-13 | 2025-01-03 | 2025-01-20 |  |  | 2025-03-24 | 2025-04-01 |  | 2025-04-14 | 2025-04-14 | 2025-06-16 |  | 2025-06-13 | 2025-06-18 | 2025-06-18 | 2025-06-25 | Pam Haber | Lisa Donmeyer | Johnathan Davila Andrew Lehman | Jamie McGlinchey | Alyssa Bostock Christina Brubaker |  | Lucie Bechu Jackie Durant Serinne Hong Ryan Welch |  | Wendy Biggs Will Turnbough |  |  |  |  | 2021-10-01
| 00164 | Hoboken-00164 | 218 Washington St Hoboken, NJ 07030 United States | NYC | 2024-02-08 | 2024-03-22 | 2024-04-02 | 2024-04-30 | 2024-04-24 | 2024-04-02 | 2024-06-20 | 2024-07-25 | 2024-08-20 | 2024-09-05 | 2024-11-26 | 2024-08-13 | 2024-10-11 | 2024-12-17 | 2025-03-20 | 2025-03-04 | 2025-03-28 | 2024-12-30 | 2025-01-28 | 2024-11-01 | 2025-03-21 | 2025-03-31 | 2025-04-15 | 2025-07-17 | 2025-06-30 | 2025-07-07 | 2025-08-05 | 2025-08-04 | 2025-08-18 | 2025-08-13 | 2025-08-13 | 2025-08-26 | Pam Haber | David Behrens Lisa Donmeyer | Johnathan Davila Andrew Lehman Alex Lundstrom | Lauren Keenoy | Alyssa Bostock |  | Lucie Bechu Jackie Durant Ryan Welch |  | Wendy Biggs Will Turnbough
| 00221 | Princeton (Route 1)-00221 | 3535 Brunswick Pike Princeton, NJ 08540 United States | NJ |  |  | 2024-03-11 | 2024-02-21 | 2024-04-01 | 2024-01-25 | 2024-06-06 | 2024-07-11 | 2024-09-24 | 2024-11-08 | 2025-04-08 | 2024-09-30 | 2024-12-19 | 2025-04-09 | 2025-06-27 | 2025-01-07 | 2025-07-07 | 2024-12-19 | 2025-01-31 | 2025-07-01 | 2025-07-01 | 2025-07-08 | 2025-07-22 | 2025-10-10 | 2025-10-07 | 2025-10-23 | 2025-10-29 | 2025-10-28 | 2025-10-28 | 2025-11-06 | 2025-11-06 | 2025-11-19 | Pam Haber | David Behrens Lisa Donmeyer | Andrew Lehman Alex Lundstrom | Lauren Keenoy | Alyssa Bostock |  | Jackie Durant Ryan Welch |  | Wendy Biggs Will Turnbough
04 - Lease Executed
| 00137 | Spring + Hudson (IK Retro)-00137 | 293 Spring Street New York, NY 10013 United States | NYM |  | 2024-09-27 | 2024-09-27 |  |  |  | 2024-11-07 | 2024-11-14 | 2024-12-17 |  | 2023-12-21 | 2024-11-20 | 2025-01-16 | 2025-01-24 | 2025-02-17 |  | 2025-02-25 | 2025-01-17 | 2025-02-10 |  |  | 2025-03-03 | 2025-03-11 | 2025-02-04 | 2025-03-19 | 2025-03-19 | 2025-04-15 |  | 2025-04-08 | 2025-04-16 | 2025-04-16 | 2025-04-18 | Pam Haber | Lisa Donmeyer | Johnathan Davila Andrew Lehman | Jamie McGlinchey | Alyssa Bostock Christina Brubaker |  |  |  | Wendy Biggs Will Turnbough |  |  |  |  | 2021-08-28
03 - Lease
| 00090 | Seaport Square (IK Retro)-00090 | 47 Northern Avenue Boston, MA 02210 United States | BOS | 2024-09-27 | 2024-09-27 | 2024-09-27 | 2023-01-24 |  |  | 2024-10-31 | 2024-11-14 | 2024-12-17 |  | 2023-12-21 | 2024-12-04 | 2025-01-30 | 2025-02-04 | 2025-04-07 |  | 2025-04-09 | 2025-01-31 | 2025-02-24 |  | 2023-03-18 | 2025-04-21 | 2025-04-29 | 2025-03-25 | 2025-05-02 | 2025-05-09 | 2025-07-08 |  | 2025-07-08 | 2025-07-09 | 2025-07-09 | 2025-07-11 | Pam Haber | Lisa Donmeyer | Johnathan Davila Andrew Lehman | Jamie McGlinchey | Alyssa Bostock Christina Brubaker |  |  |  | Wendy Biggs Will Turnbough
| 00256 | Lower East Side-00256 | 167 Orchard St New York, NY 10002 United States | NYC | 2024-08-01 | 2024-09-04 | 2024-09-20 | 2024-09-24 | 2024-09-05 | 2024-09-20 | 2024-10-31 | 2024-11-28 | 2024-12-17 | 2025-01-13 |  | 2024-12-06 | 2025-01-31 | 2025-02-07 | 2025-03-04 | 2025-10-28 | 2025-03-12 | 2025-02-03 | 2025-03-04 | 2025-03-17 | 2025-03-17 | 2025-03-31 | 2025-04-15 | 2025-07-03 | 2025-06-16 | 2025-06-23 | 2025-07-22 | 2025-07-21 | 2025-07-21 | 2025-07-30 | 2025-07-30 | 2025-08-12 | Pam Haber | Lisa Donmeyer Whitney Schmidt | Andrew Lehman | Lauren Keenoy | Alyssa Bostock |  | Lucie Bechu Ridhima Chhibber Jackie Durant Serinne Hong Hsienting Huang Jesus Verastegui Ryan Welch |  | Wendy Biggs Will Turnbough
| 00303 | Union Square Relo (870 Broadway) (RELO)-00303 | 870 Broadway New York, NY 10003 United States | NYC | 2024-07-01 | 2024-08-29 | 2024-08-13 | 2024-09-24 | 2024-08-21 | 2024-08-27 | 2024-10-17 | 2024-11-14 | 2025-02-03 | 2025-02-12 | 2025-07-08 | 2024-11-22 | 2025-01-17 | 2025-07-09 | 2025-08-07 |  | 2025-08-15 | 2025-06-16 | 2025-07-29 | 2025-02-13 | 2025-02-13 | 2025-08-25 | 2025-09-09 | 2025-11-17 | 2025-11-11 | 2025-11-26 | 2025-12-16 | 2025-12-15 | 2025-12-15 | 2025-12-24 | 2025-12-24 | 2026-01-06 | Pam Haber | Lisa Donmeyer | Johnathan Davila Andrew Lehman | Jamie McGlinchey | Alyssa Bostock Christina Brubaker |  | Lucie Bechu Jackie Durant Ryan Welch |  | Wendy Biggs Will Turnbough
| 00296 | Framingham-00296 | 1 Worcester Rd Framingham, MA 01701 United States | BOS | 2024-06-18 | 2024-06-28 | 2024-09-30 | 2024-07-16 | 2024-10-10 | 2024-07-29 | 2024-11-07 | 2024-12-05 | 2024-12-17 | 2024-12-19 | 2025-04-18 | 2024-12-06 | 2025-01-31 | 2025-04-21 | 2025-06-18 | 2025-11-18 | 2025-06-26 | 2025-02-03 | 2025-03-04 | 2025-01-29 | 2025-01-29 | 2025-10-24 | 2025-11-10 | 2026-02-11 | 2026-01-23 | 2026-01-30 | 2026-03-02 | 2026-02-27 | 2026-02-27 | 2026-03-10 | 2026-03-10 | 2026-03-23 | Pam Haber | Lisa Donmeyer | Johnathan Davila Andrew Lehman | Jamie McGlinchey | Alyssa Bostock Christina Brubaker |  | Kathryn Grotheer Seungeun Lee Sara Nobes |  | Wendy Biggs Will Turnbough |  |  |  | Ruggles Sign
| 00316 | Millbury-00316 | 70 Worcester-Providence Turnpike Millbury, MA 01527 United States | BOS | 2024-05-09 | 2024-09-17 | 2024-09-20 | 2024-08-20 | 2026-05-11 | 2024-09-19 | 2024-10-24 | 2024-12-19 | 2025-01-21 | 2025-01-24 |  | 2025-08-04 | 2025-09-29 | 2025-10-06 | 2025-11-19 | 2026-04-04 | 2025-11-27 | 2025-09-30 | 2025-10-29 | 2026-06-02 | 2026-06-02 | 2026-06-15 | 2026-06-30 | 2026-09-17 | 2026-08-31 | 2026-09-07 | 2026-10-06 | 2026-10-05 | 2026-10-05 | 2026-10-14 | 2026-10-14 | 2026-10-27 | Pam Haber | Lisa Donmeyer | Johnathan Davila Andrew Lehman | Jamie McGlinchey | Alyssa Bostock Christina Brubaker |  |  |  | Wendy Biggs Will Turnbough